## Dashboard
SOC 2 CONTROL MAPPING — COMPLIANCE DASHBOARD
Acme Technologies, Inc. ¦ Prepared by: Kunj Patel, GRC Analyst ¦ Assessment Period: FY2025 ¦ Last Updated: March 2026
OVERALL COMPLIANCE SUMMARY
Total Controls | Implemented | In Progress | Planned | Not Implemented | Overall Score
25 | 15 | 7 | 2 | 1
COMPLIANCE BY TSC CATEGORY
TSC Category | Total Controls | Implemented | In Progress | Planned / Gap | % Complete | Status
CC – Common Criteria | 20 | 13 | 5 | 2 |  | On Track
A – Availability | 3 | 2 | 1 | 0 |  | On Track
C – Confidentiality | 2 | 1 | 1 | 0 |  | On Track
PI – Processing Integrity | 0 | 0 | 0 | 0 | N/A | Not Started
P – Privacy | 0 | 0 | 0 | 0 | N/A | Not Started
TOP GAPS REQUIRING ATTENTION
TSC ID | Criteria | Gap Description | Owner | Status | Target Date | Priority
CC6.6 | Logical Access – MFA | MFA not enforced for 100% of remote users | IT Security Lead | In Progress | 30 days | CRITICAL
CC6.7 | DLP Controls | DLP controls not fully deployed across all data stores | IT Security Lead | Planned | Q2 2026 | HIGH
CC7.2 | SIEM Monitoring | SIEM coverage incomplete; not all critical systems logging | IT Security Lead | In Progress | Q2 2026 | HIGH
CC9.1 | Vendor Risk Management | Formal TPRM program not yet fully implemented | GRC Analyst | In Progress | Q2 2026 | HIGH
CC3.3 | Fraud Risk Assessment | Fraud risk not assessed as a standalone process | GRC / HR | In Progress | Q2 2026 | MEDIUM
A1.3 | Disaster Recovery Testing | DR test overdue; last performed 6 months ago | IT Manager | Planned | Q2 2026 | MEDIUM
C1.2 | Data Retention | Formal data retention schedule not implemented across all systems | IT Manager | In Progress | Q2 2026 | MEDIUM

## Overview
SOC 2 TRUST SERVICE CRITERIA — CONTROL MAPPING WORKBOOK
Acme Technologies, Inc. ¦ Prepared by: Kunj Patel, GRC Analyst ¦ Assessment Period: January 1 – December 31, 2025 ¦ Version: 1.0
PURPOSE | This workbook maps Acme Technologies security controls to the AICPA SOC 2 Trust Service Criteria (TSC). Each tab covers one TSC category. Use this workbook to track control implementation status, identify gaps, and prepare evidence for SOC 2 audits.
TSC CATEGORIES COVERED
TSC Category | Description | Workbook Tab | Criteria Count
CC – Common Criteria | Security controls required for all SOC 2 reports | CC Sheet | 9 criteria
A – Availability | System availability commitments and uptime | A Sheet | 3 criteria
C – Confidentiality | Protection of confidential information | C Sheet | 2 criteria
PI – Processing Integrity | Complete, valid, accurate processing | PI Sheet | 5 criteria
P – Privacy | Collection, use, and retention of personal data | P Sheet | 8 criteria
STATUS LEGEND
Implemented | Control is fully in place and operating effectively
In Progress | Control is being implemented; partially in place
Planned | Control is planned but not yet started
Not Implemented | Control is not in place; represents a gap requiring remediation
N/A | Control criterion is not applicable to this environment

## CC - Common Criteria
SOC 2 — COMMON CRITERIA (CC) CONTROL MAPPING
Acme Technologies, Inc. ¦ GRC Analyst: Kunj Patel ¦ Assessment Period: FY2025 ¦ Framework: AICPA SOC 2 TSC 2017
# | TSC ID | TSC Criteria Name | TSC Requirement Summary | Acme Control Description | Control Evidence / Artifact | Control Owner | Implementation Status | Gap / Remediation Notes | NIST CSF Mapping | Target Completion
1 | CC1.1 | Control Environment – COSO Principles | Entity demonstrates commitment to integrity and ethical values | Code of Conduct policy enforced; annual acknowledgement required of all employees. Ethics hotline available. | Signed Code of Conduct acknowledgements; HR onboarding records; ethics hotline logs | HR / Legal | Implemented | No gaps identified | ID.GV-1 | —
2 | CC1.2 | Board Oversight | Board of directors demonstrates independence and exercises oversight of internal controls | Executive leadership reviews quarterly security reports; CISO presents to board annually | Board meeting minutes; CISO quarterly report deck; security KPI dashboard | CISO | Implemented | No gaps identified | ID.GV-2 | —
3 | CC2.1 | Information and Communication – Internal | Entity obtains or generates quality information to support internal controls | SIEM deployed for log aggregation; security dashboards reviewed weekly by IT Security Lead | SIEM configuration; alert rule documentation; weekly review meeting notes | IT Security Lead | Implemented | Expand SIEM log sources to cover all critical systems | DE.CM-1 | Q2 2026
4 | CC2.2 | Information and Communication – External | Entity communicates externally about matters affecting internal controls | Security disclosure policy documented; customers notified of material incidents per SLA; privacy policy published | Incident notification templates; customer SLA agreements; published privacy policy URL | GRC / Legal | Implemented | No gaps identified | RS.CO-2 | —
5 | CC3.1 | Risk Assessment – Objectives | Entity specifies objectives with sufficient clarity to identify and assess risks | Annual information security risk assessment conducted using NIST CSF; results reviewed by CISO | Annual Risk Assessment Report (IS-RA-001); CISO sign-off documentation | GRC Analyst | Implemented | No gaps identified | ID.RA-1 | —
6 | CC3.2 | Risk Assessment – Risk Identification | Entity identifies risks to achievement of its objectives | Risk register maintained and updated quarterly; risks scored by likelihood and impact using 5x5 matrix | Risk register (IS-RA-001); quarterly risk review meeting notes; risk scoring methodology doc | GRC Analyst | Implemented | No gaps identified | ID.RA-3 | —
7 | CC3.3 | Risk Assessment – Fraud Risk | Entity considers potential for fraud in assessing risks | Fraud risk factors reviewed during annual risk assessment; background checks for all new hires | Risk assessment fraud section; HR background check policy; vendor screening records | GRC / HR | In Progress | Formal fraud risk assessment process not yet documented separately | ID.RA-5 | Q2 2026
8 | CC4.1 | Monitoring – Evaluation of Controls | Entity selects, develops, and performs evaluations of internal controls | Annual internal controls review; quarterly vulnerability scans; SOC 2 readiness assessment conducted | Vulnerability scan reports; internal audit findings; SOC 2 readiness assessment report | GRC Analyst | Implemented | No gaps identified | ID.RA-6 | —
9 | CC5.1 | Control Activities – Mitigation of Risks | Entity selects and develops control activities that mitigate risks | Control activities mapped to risk register; compensating controls documented where primary controls are unavailable | Risk register with control mapping; compensating controls log; control testing results | GRC Analyst | Implemented | No gaps identified | PR.IP-1 | —
10 | CC6.1 | Logical Access – Boundaries | Entity implements logical access security measures to protect against threats | Firewalls, IDS/IPS, and network segmentation implemented; access logs reviewed monthly | Firewall configuration docs; IDS alert logs; network topology diagram; monthly access reviews | IT Security Lead | In Progress | Network segmentation (VLANs) planned but not fully implemented | PR.AC-5 | Q3 2026
11 | CC6.2 | Logical Access – Registration and Authorization | Prior to granting access, entity registers and authorizes new users | Formal access provisioning process via IT ticketing system; manager approval required for all new access | Access request tickets; manager approval records; provisioning SOPs | IT Manager | Implemented | No gaps identified | PR.AC-1 | —
12 | CC6.3 | Logical Access – Role-Based Access | Entity removes access when no longer needed | RBAC enforced via Active Directory; quarterly access reviews; automated deprovisioning on termination | AD group policy configs; quarterly access review reports; offboarding checklist records | IT Manager | Implemented | No gaps identified | PR.AC-4 | —
13 | CC6.6 | Logical Access – Threats from Outside System Boundaries | Entity implements controls to prevent unauthorized access from outside system boundaries | MFA enforced for all remote access; VPN required for external connections; external vulnerability scans monthly | MFA enforcement policy; VPN logs; external vulnerability scan reports | IT Security Lead | In Progress | MFA not yet enforced for 100% of remote users — remediation in progress | PR.AC-7 | 30 days
14 | CC6.7 | Logical Access – Transmission and Removal of Information | Entity restricts transmission, movement, and removal of information to authorized users | DLP controls deployed on M365; removable media policy enforced; data transfer logging enabled | DLP policy config; removable media approval logs; data transfer audit logs | IT Security Lead | Planned | DLP controls partially deployed; full coverage planned | PR.DS-2 | Q2 2026
15 | CC7.1 | System Operations – Vulnerability Management | Entity detects and monitors for new vulnerabilities on an ongoing basis | Monthly vulnerability scans using approved scanning tool; critical findings remediated within 7 days | Vulnerability scan reports; remediation tracking tickets; patch management policy | IT Security Lead | Implemented | No gaps identified | PR.IP-12 | —
16 | CC7.2 | System Operations – Monitoring | Entity monitors system components and operations for anomalies | SIEM monitors all critical systems; automated alerts configured for high-priority events; reviewed daily | SIEM alert configuration; daily review log; incident tickets created from alerts | IT Security Lead | In Progress | SIEM coverage incomplete — expansion in progress | DE.CM-7 | Q2 2026
17 | CC7.3 | System Operations – Incident Evaluation | Entity evaluates security events to determine if they are incidents | Incident response runbooks define classification criteria; all security events triaged within 4 hours | Incident Response Policy (IS-POL-003); incident triage log; severity classification matrix | IT Security Lead | Implemented | No gaps identified | RS.AN-1 | —
18 | CC8.1 | Change Management – Authorized Changes | Entity authorizes, designs, develops, configures, documents, tests, approves, and implements changes | Change management process documented; all changes require CAB approval; tested in staging before production | Change management SOP; CAB meeting minutes; change request tickets; test results | IT Manager | Implemented | No gaps identified | PR.IP-3 | —
19 | CC9.1 | Risk Mitigation – Vendor Risk | Entity identifies, selects, and develops risk mitigation for business disruption | Third-party risk management program in development; top vendors assessed annually for security posture | TPRM program documentation; vendor security questionnaires; vendor risk scores | GRC Analyst | In Progress | Formal TPRM program not yet fully implemented | ID.SC-2 | Q2 2026
20 | CC9.2 | Risk Mitigation – Business Continuity | Entity assesses and manages risks associated with vendors and business partners | Business continuity plan documented; disaster recovery tested annually; RTO/RPO defined per system | BCP document; DR test results; RTO/RPO documentation; backup verification logs | IT Manager | Implemented | DR test last performed 6 months ago — schedule next test | RC.RP-1 | Q2 2026

## A - Availability
SOC 2 — AVAILABILITY (A) CONTROL MAPPING
Acme Technologies, Inc. ¦ GRC Analyst: Kunj Patel ¦ Assessment Period: FY2025
# | TSC ID | TSC Criteria Name | TSC Requirement Summary | Acme Control Description | Control Evidence / Artifact | Control Owner | Implementation Status | Gap / Remediation Notes | NIST CSF Mapping | Target Completion
1 | A1.1 | Availability – Performance Monitoring | Entity maintains, monitors, and evaluates current processing capacity and use to manage capacity demand | System performance monitored via Azure Monitor and SIEM; capacity thresholds alert at 80%; reviewed weekly | Azure Monitor dashboards; capacity alert configs; weekly review meeting notes; uptime reports | Cloud Engineer | Implemented | No gaps identified | DE.CM-1 | —
2 | A1.2 | Availability – Environmental Threats | Entity authorizes, designs, develops, configures, documents, tests, approves, and implements changes to infrastructure | AWS multi-AZ deployment; redundant network paths; UPS and generator at primary data center | AWS architecture diagram; redundancy design docs; UPS maintenance records; DR test results | Cloud Engineer | Implemented | No gaps identified | PR.IP-9 | —
3 | A1.3 | Availability – Recovery | Entity recovers and resumes system operations after disruption | Disaster recovery plan tested annually; backup restoration tested quarterly; RTO < 4hrs, RPO < 1hr for critical systems | DR plan document; annual DR test report; backup restoration test logs; RTO/RPO SLA documentation | IT Manager | In Progress | Last DR test was 6 months ago — next test scheduled Q2 2026 | RC.RP-1 | Q2 2026

## C - Confidentiality
SOC 2 — CONFIDENTIALITY (C) CONTROL MAPPING
Acme Technologies, Inc. ¦ GRC Analyst: Kunj Patel ¦ Assessment Period: FY2025
# | TSC ID | TSC Criteria Name | TSC Requirement Summary | Acme Control Description | Control Evidence / Artifact | Control Owner | Implementation Status | Gap / Remediation Notes | NIST CSF Mapping | Target Completion
1 | C1.1 | Confidentiality – Identification | Entity identifies and maintains confidential information to meet objectives | Data classification policy defines Confidential and Restricted tiers; all data assets labeled; DLP monitors sensitive data | Data Classification Policy (IS-POL-004); data asset inventory; DLP configuration and alert logs | GRC Analyst | Implemented | No gaps identified | PR.DS-1 | —
2 | C1.2 | Confidentiality – Disposal | Entity disposes of confidential information to meet objectives | Secure data disposal procedures documented; hardware wiped using DoD 5220.22-M standard before disposal; retention schedule enforced | Data disposal SOP; hardware disposal certificates; data retention schedule; disposal vendor contracts | IT Manager | In Progress | Formal data retention schedule not yet fully implemented across all systems | PR.IP-6 | Q2 2026